## Quarterly
Week | Task | Difficulty
CW 27 | Understand requirements of ML application | Medium
CW 28 | Prepare setting up the environment by gathering necessary rights and authorisations (e.g. in GitHub, Azure..) | Easy
CW 29 | Make project plan and discuss feasibility with team (e.g. application developer) | Medium
CW 30 | Finalise project plan and set up trello task board | Medium
CW 31 | Start setting up the environment by doing a test run using GitHub Actions as build server | Medium
CW 32 | Set up continous delivery workflow with Azure Pipeines | Medium
CW 33 | Set up continous delivery workflow with Azure Pipeines | Medium
CW 34 | Demo work with team and reassure with developer that needs of the application are met | Hard
CW 35 | Add/improve CD workflow and add effective alerts | Medium
CW 36 | CI/CD Pipeline ready for QA | Medium
CW 37 | (Time buffer) | Easy
CW 38 | (Time buffer) | Easy
Goals
Deploy ML application with CI/CD pipeline
Have logging and effective alerts in place for effective CD

## Yearly
Week | Task | Difficulty
CW 1 | Enhance knowledge on cloud computing concepts | Easy
CW 2 | Enhance knowledge on cloud computing concepts | Easy
CW 3 | Enhance knowledge on cloud computing concepts | Easy
CW 4 | Enhance knowledge on DevOps principles | Easy
CW 5 | Enhance knowledge on DevOps principles | Easy
CW 6 | Enhance knowledge of ML application development | Easy
CW 7 | Enhance knowledge of ML application development | Easy
CW 8 | Enhance knowledge of ML application development | Easy
CW 9 | Enhance knowledge on tools such as Docker, Kubernetes, Microservices strategy | Easy
CW 10 | Enhance knowledge on tools such as Docker, Kubernetes, Microservices strategy | Easy
CW 11 | Enhance knowledge on tools such as Docker, Kubernetes, Microservices strategy | Easy
CW 12 | Get familiar with Azure platform | Easy
CW 13 | Get familiar with Azure platform | Easy
CW 14 | Get overview of tools for deploying CI/CD pipelines | Easy
CW 15 | Get overview of tools for deploying CI/CD pipelines | Easy
CW 16 | Get overview of tools for deploying CI/CD pipelines | Easy
CW 17 | Get overview of tools for deploying CI/CD pipelines | Easy
CW 18 | Get familiar with Azure platform | Easy
CW 19 | Get familiar with Azure platform | Easy
CW 20 | Get familiar with Azure Dev platform | Easy
CW 21 | Get familiar with Azure Dev platform | Easy
CW 22 | Get familiar with Azure Web Services | Easy
CW 23 | Enhance knowledge of writing yml code | Medium
CW 24 | Enhance knowledge of writing yml code | Medium
CW 25 | Enhance knowledge of writing yml code | Medium
CW 26 | Enhance knowledge of writing yml code | Medium
CW 27 | Understand requirements of ML application | Medium
CW 28 | Prepare setting up the environment by gathering necessary rights and authorisations (e.g. in GitHub, Azure..) | Easy
CW 29 | Make project plan and discuss feasibility with team (e.g. application developer) | Medium
CW 30 | Finalise project plan and set up trello task board | Medium
CW 31 | Start setting up the environment by doing a test run using GitHub Actions as build server | Medium
CW 32 | Set up continous delivery workflow with Azure Pipeines | Medium
CW 33 | Set up continous delivery workflow with Azure Pipeines | Medium
CW 34 | Demo work with team and reassure with developer that needs of the application are met | Hard
CW 35 | Add/improve CD workflow and add effective alerts | Medium
CW 36 | CI/CD Pipeline ready for QA | Medium
CW 37 | (Time buffer) | Easy
CW 38 | (Time buffer) | Easy
CW 39 | Deploy CI/CD pipeline | Medium
CW 40 | Team gathering for feedback to evaluate project on running CI/CD pipeline | Hard
CW 41 | Set the scene for starting with improvements of CI/CD pipelines | Medium
CW 42 | Continuous improvement of the CI/CD pipeline | Medium
CW 43 | Continuous improvement of the CI/CD pipeline | Medium
CW 44 | Continuous improvement of the CI/CD pipeline | Medium
CW 45 | Continuous improvement of the CI/CD pipeline | Medium
CW 46 | Continuous improvement of the CI/CD pipeline | Medium
CW 47 | Continuous improvement of the CI/CD pipeline | Medium
CW 48 | Continuous improvement of the CI/CD pipeline | Medium
CW 49 | Continuous improvement of the CI/CD pipeline | Medium
CW 50 | Year review with team | Hard
CW 51 | Team time | Easy
CW 52 | Team time | Easy
Goals
Deploy ML application with CI/CD pipeline
Have logging and effective alerts in place for effective CD
Enhance knowledge and skills to be able to effectively deploy CI/CD pipelines
Improve CI/CD pipeline where necessary